## Dashboard
Construction Finance Dashboard
Prairie Field Services Ltd. ¦ Results through 31-Aug-26 ¦ CAD
Selected case | Base
Revised cost budget |  | Estimate at completion |  | Cost variance |  | Projected gross profit |  | Gross margin |  | Ending cash
7225000 |  | 7390000 |  | -165000 |  | 2015000 |  | 21.42% |  | 105000
Project | Status | Revised Budget | EAC | Cost Variance | Contract Revenue | Gross Profit | Gross Margin | Outstanding AR | Management Attention
Substation Equipment Replacement | In Progress | 1620000 | 1675000 | -55000 | 2105000 | 430000 | 20.43% | 250000 | Cost overrun
Natural Gas Pipeline Inspection | In Progress | 1180000 | 1150000 | 30000 | 1545000 | 395000 | 25.57% | 190000 | On track
Rural Power-Line Upgrade | Delayed | 2010000 | 2130000 | -120000 | 2610000 | 480000 | 18.39% | 220000 | Cost overrun
Compressor Station Maintenance | In Progress | 990000 | 975000 | 15000 | 1275000 | 300000 | 23.53% | 120000 | On track
Fleet Garage Construction | Delayed | 1425000 | 1460000 | -35000 | 1870000 | 410000 | 21.93% | 220000 | Cost overrun
Portfolio |  | 7225000 | 7390000 | -165000 | 9405000 | 2015000 | 21.42% | 1000000
Week | Ending Cash | [9 empty] | Week | Ending Cash
2026-09-07 | 1140000 | [9 empty] | 7-Sep | 1140000
2026-09-14 | 1100000 | [9 empty] | 14-Sep | 1100000
2026-09-21 | 1025000 | [9 empty] | 21-Sep | 1025000
2026-09-28 | 920000 | [9 empty] | 28-Sep | 920000
2026-10-05 | 805000 | [9 empty] | 5-Oct | 805000
2026-10-12 | 745000 | [9 empty] | 12-Oct | 745000
2026-10-19 | 675000 | [9 empty] | 19-Oct | 675000
2026-10-26 | 580000 | [9 empty] | 26-Oct | 580000
2026-11-02 | 465000 | [9 empty] | 2-Nov | 465000
2026-11-09 | 375000 | [9 empty] | 9-Nov | 375000
2026-11-16 | 265000 | [9 empty] | 16-Nov | 265000
2026-11-23 | 180000 | [9 empty] | 23-Nov | 180000
2026-11-30 | 105000 | [9 empty] | 30-Nov | 105000

## Assumptions
Assumptions
Select one case. Yellow cells with blue text are editable.
Case selector | 2 |  | Selector key
Selected case | Base |  | 1 | Best
Starting cash | 1200000 |  | 2 | Base
|  |  | 3 | Worst
Remaining project cost adjustment | Active selection | 0%
| Best | -5%
| Base | 0%
| Worst | 12%
Customer receipt factor | Active selection | 100%
| Best | 105%
| Base | 100%
| Worst | 85%
Vendor payment factor | Active selection | 100%
| Best | 97%
| Base | 100%
| Worst | 108%
Payroll and overhead factor | Active selection | 100%
| Best | 98%
| Base | 100%
| Worst | 105%
Model note | The active case changes project cost forecasts and the 13-week cash forecast.
Reporting date | 2026-08-31

## Financial Model
Project Financial Model
Forecast at completion, profitability, billing and receivables by project
Selected case | Base
Reporting date | 2026-08-31
Project ID | Project Name | Industry | Revised Cost Budget | Actual Cost to Date | Open Commitments | Estimate to Complete | Estimate at Completion | Cost Variance | Revised Contract Revenue | Projected Gross Profit | Gross Margin | Client Billings | Cash Collected | Outstanding Receivables | Revenue Recognized | Unbilled Revenue | Completion % | Project Status | Management Attention
P-101 | Substation Equipment Replacement | Utility | 1620000 | 1025000 | 300000 | 650000 | 1675000 | -55000 | 2105000 | 430000 | 20.43% | 1200000 | 950000 | 250000 | 1368250 | 168250 | 65% | In Progress | Cost overrun
P-102 | Natural Gas Pipeline Inspection | Oil & Gas | 1180000 | 820000 | 230000 | 330000 | 1150000 | 30000 | 1545000 | 395000 | 25.57% | 1050000 | 860000 | 190000 | 1112400 | 62400 | 72% | In Progress | On track
P-103 | Rural Power-Line Upgrade | Utility | 2010000 | 1150000 | 510000 | 980000 | 2130000 | -120000 | 2610000 | 480000 | 18.39% | 1350000 | 1130000 | 220000 | 1513800 | 163800 | 58% | Delayed | Cost overrun
P-104 | Compressor Station Maintenance | Oil & Gas | 990000 | 800000 | 120000 | 175000 | 975000 | 15000 | 1275000 | 300000 | 23.53% | 950000 | 830000 | 120000 | 1058250 | 108250 | 83% | In Progress | On track
P-105 | Fleet Garage Construction | Construction | 1425000 | 700000 | 420000 | 760000 | 1460000 | -35000 | 1870000 | 410000 | 21.93% | 860000 | 640000 | 220000 | 916300 | 56300 | 49% | Delayed | Cost overrun
TOTAL | Portfolio |  | 7225000 | 4495000 | 1580000 | 2895000 | 7390000 | -165000 | 9405000 | 2015000 | 21.42% | 5410000 | 4410000 | 1000000 | 5969000 | 559000 | 63.51%

## Cash Forecast
13-Week Cash Forecast
Company-level cash forecast driven by the selected scenario
Selected case | Base
Forecast start | 2026-09-07
Cash flow item | Type | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30
Beginning cash | Calculated | 1200000 | 1140000 | 1100000 | 1025000 | 920000 | 805000 | 745000 | 675000 | 580000 | 465000 | 375000 | 265000 | 180000
Base customer receipts | Input | 420000 | 310000 | 510000 | 275000 | 460000 | 350000 | 540000 | 295000 | 480000 | 330000 | 525000 | 360000 | 600000
Forecast customer receipts | Calculated | 420000 | 310000 | 510000 | 275000 | 460000 | 350000 | 540000 | 295000 | 480000 | 330000 | 525000 | 360000 | 600000
Base vendor payments | Input | 300000 | 255000 | 410000 | 280000 | 390000 | 315000 | 430000 | 290000 | 405000 | 325000 | 450000 | 340000 | 470000
Forecast vendor payments | Calculated | 300000 | 255000 | 410000 | 280000 | 390000 | 315000 | 430000 | 290000 | 405000 | 325000 | 450000 | 340000 | 470000
Base payroll and overhead | Input | 180000 | 95000 | 175000 | 100000 | 185000 | 95000 | 180000 | 100000 | 190000 | 95000 | 185000 | 105000 | 205000
Forecast payroll and overhead | Calculated | 180000 | 95000 | 175000 | 100000 | 185000 | 95000 | 180000 | 100000 | 190000 | 95000 | 185000 | 105000 | 205000
Net cash flow | Calculated | -60000 | -40000 | -75000 | -105000 | -115000 | -60000 | -70000 | -95000 | -115000 | -90000 | -110000 | -85000 | -75000
Ending cash | Calculated | 1140000 | 1100000 | 1025000 | 920000 | 805000 | 745000 | 675000 | 580000 | 465000 | 375000 | 265000 | 180000 | 105000

## Project Master
Project Master
Fictional construction, utility and oil and gas projects
Project ID | Project Name | Industry | Project Manager | Location | Start Date | Expected End Date | Original Cost Budget | Approved Cost Change Orders | Original Contract Revenue | Approved Revenue Change Orders | Completion % | Project Status | Base Estimate to Complete
P-101 | Substation Equipment Replacement | Utility | Maya Chen | Regina, SK | 2026-01-15 | 2026-12-15 | 1500000 | 120000 | 1950000 | 155000 | 65% | In Progress | 650000
P-102 | Natural Gas Pipeline Inspection | Oil & Gas | Daniel Brooks | Calgary, AB | 2026-03-01 | 2026-10-31 | 1100000 | 80000 | 1450000 | 95000 | 72% | In Progress | 330000
P-103 | Rural Power-Line Upgrade | Utility | Priya Shah | Moose Jaw, SK | 2026-02-10 | 2026-11-30 | 1800000 | 210000 | 2350000 | 260000 | 58% | Delayed | 980000
P-104 | Compressor Station Maintenance | Oil & Gas | Ethan Cole | Edmonton, AB | 2026-04-01 | 2026-09-30 | 950000 | 40000 | 1220000 | 55000 | 83% | In Progress | 175000
P-105 | Fleet Garage Construction | Construction | Sophia Martin | Regina, SK | 2026-01-05 | 2026-12-20 | 1250000 | 175000 | 1650000 | 220000 | 49% | Delayed | 760000

## Transactions
Transactions
Fictional invoice, accrual, commitment, billing and cash receipt records through 31-Aug-26
Transaction ID | Transaction Date | Project ID | Transaction Type | Cost Category | Counterparty | Status | Amount
TX-0001 | 2026-02-08 | P-101 | Vendor Invoice | Materials | Prairie Steel Ltd. | Approved | 210000
TX-0002 | 2026-03-08 | P-101 | Vendor Invoice | Electrical | Western Electrical Services | Approved | 185000
TX-0003 | 2026-04-08 | P-101 | Vendor Invoice | Civil | Northern Civil Works | Approved | 160000
TX-0004 | 2026-05-08 | P-101 | Vendor Invoice | Equipment | Summit Equipment Rentals | Approved | 235000
TX-0005 | 2026-06-08 | P-101 | Vendor Invoice | Engineering | Frontier Engineering Group | Approved | 150000
TX-0006 | 2026-08-28 | P-101 | Accrual | Month-end Accrual | Frontier Engineering Group | Recorded | 85000
TX-0007 | 2026-08-31 | P-101 | Commitment | Open Purchase Order | Northern Civil Works | Open | 300000
TX-0008 | 2026-05-15 | P-101 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 650000
TX-0009 | 2026-07-15 | P-101 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 550000
TX-0010 | 2026-06-20 | P-101 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 500000
TX-0011 | 2026-08-20 | P-101 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 450000
TX-0012 | 2026-02-09 | P-102 | Vendor Invoice | Materials | Prairie Steel Ltd. | Approved | 180000
TX-0013 | 2026-03-09 | P-102 | Vendor Invoice | Electrical | Western Electrical Services | Approved | 165000
TX-0014 | 2026-04-09 | P-102 | Vendor Invoice | Civil | Northern Civil Works | Approved | 155000
TX-0015 | 2026-05-09 | P-102 | Vendor Invoice | Equipment | Summit Equipment Rentals | Approved | 170000
TX-0016 | 2026-06-09 | P-102 | Vendor Invoice | Engineering | Frontier Engineering Group | Approved | 105000
TX-0017 | 2026-08-27 | P-102 | Accrual | Month-end Accrual | Frontier Engineering Group | Recorded | 45000
TX-0018 | 2026-08-31 | P-102 | Commitment | Open Purchase Order | Northern Civil Works | Open | 230000
TX-0019 | 2026-05-16 | P-102 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 580000
TX-0020 | 2026-07-16 | P-102 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 470000
TX-0021 | 2026-06-21 | P-102 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 500000
TX-0022 | 2026-08-21 | P-102 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 360000
TX-0023 | 2026-02-10 | P-103 | Vendor Invoice | Materials | Prairie Steel Ltd. | Approved | 250000
TX-0024 | 2026-03-10 | P-103 | Vendor Invoice | Electrical | Western Electrical Services | Approved | 220000
TX-0025 | 2026-04-10 | P-103 | Vendor Invoice | Civil | Northern Civil Works | Approved | 210000
TX-0026 | 2026-05-10 | P-103 | Vendor Invoice | Equipment | Summit Equipment Rentals | Approved | 190000
TX-0027 | 2026-06-10 | P-103 | Vendor Invoice | Engineering | Frontier Engineering Group | Approved | 170000
TX-0028 | 2026-08-26 | P-103 | Accrual | Month-end Accrual | Frontier Engineering Group | Recorded | 110000
TX-0029 | 2026-08-31 | P-103 | Commitment | Open Purchase Order | Northern Civil Works | Open | 510000
TX-0030 | 2026-05-17 | P-103 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 750000
TX-0031 | 2026-07-17 | P-103 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 600000
TX-0032 | 2026-06-22 | P-103 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 650000
TX-0033 | 2026-08-22 | P-103 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 480000
TX-0034 | 2026-02-11 | P-104 | Vendor Invoice | Materials | Prairie Steel Ltd. | Approved | 175000
TX-0035 | 2026-03-11 | P-104 | Vendor Invoice | Electrical | Western Electrical Services | Approved | 160000
TX-0036 | 2026-04-11 | P-104 | Vendor Invoice | Civil | Northern Civil Works | Approved | 145000
TX-0037 | 2026-05-11 | P-104 | Vendor Invoice | Equipment | Summit Equipment Rentals | Approved | 155000
TX-0038 | 2026-06-11 | P-104 | Vendor Invoice | Engineering | Frontier Engineering Group | Approved | 120000
TX-0039 | 2026-08-25 | P-104 | Accrual | Month-end Accrual | Frontier Engineering Group | Recorded | 45000
TX-0040 | 2026-08-31 | P-104 | Commitment | Open Purchase Order | Northern Civil Works | Open | 120000
TX-0041 | 2026-05-18 | P-104 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 520000
TX-0042 | 2026-07-18 | P-104 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 430000
TX-0043 | 2026-06-23 | P-104 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 480000
TX-0044 | 2026-08-23 | P-104 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 350000
TX-0045 | 2026-02-12 | P-105 | Vendor Invoice | Materials | Prairie Steel Ltd. | Approved | 140000
TX-0046 | 2026-03-12 | P-105 | Vendor Invoice | Electrical | Western Electrical Services | Approved | 130000
TX-0047 | 2026-04-12 | P-105 | Vendor Invoice | Civil | Northern Civil Works | Approved | 125000
TX-0048 | 2026-05-12 | P-105 | Vendor Invoice | Equipment | Summit Equipment Rentals | Approved | 110000
TX-0049 | 2026-06-12 | P-105 | Vendor Invoice | Engineering | Frontier Engineering Group | Approved | 105000
TX-0050 | 2026-08-24 | P-105 | Accrual | Month-end Accrual | Frontier Engineering Group | Recorded | 90000
TX-0051 | 2026-08-31 | P-105 | Commitment | Open Purchase Order | Northern Civil Works | Open | 420000
TX-0052 | 2026-05-19 | P-105 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 500000
TX-0053 | 2026-07-19 | P-105 | Client Billing | Progress Billing | Prairie Energy Client | Issued | 360000
TX-0054 | 2026-06-24 | P-105 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 390000
TX-0055 | 2026-08-24 | P-105 | Cash Receipt | Customer Collection | Prairie Energy Client | Received | 250000

## Model Checks
Model Checks
Control totals and roll-forward checks. Differences should equal 0.00.
Check | Model Total | Independent Total | Difference | Status
Actual project costs | 4495000 | 4495000 | 0 | OK
Client billings | 5410000 | 5410000 | 0 | OK
Cash collected | 4410000 | 4410000 | 0 | OK
Revised cost budget | 7225000 | 7225000 | 0 | OK
Cash roll-forward | 0 | 0 | 0 | OK

## Guide
Model Guide
Portfolio workbook for construction, utility and energy finance roles
Section | Details
Company | Prairie Field Services Ltd. is a fictional contractor serving utility and energy clients.
Purpose | Demonstrate project accounting, financial modelling, cash forecasting, billing, receivables and management reporting.
Data policy | All names, transactions, amounts and assumptions are fictional. No current or former employer information is included.
How to use | Choose case 1, 2 or 3 on Assumptions. Update yellow cells with blue text. Review Dashboard, Financial Model and Cash Forecast.
Best case | Lower remaining project costs, stronger customer receipts and lower vendor and overhead payments.
Base case | Current estimate and payment assumptions.
Worst case | Higher remaining project costs, slower customer receipts and higher vendor and overhead payments.
Key outputs | Estimate at completion, cost variance, projected gross profit, gross margin, outstanding receivables and 13-week ending cash.